## BOQ Summary
BILL OF QUANTITIES - Al Nakheel Tower Construction Project
Project No: ANT-2024-0087 ¦ Client: Al Nakheel Development Co. ¦ Location: Riyadh, KSA
Date: 15-Mar-2024 ¦ Rev: 03 ¦ Currency: SAR (Saudi Riyal)
Item No. | Description | Unit | Quantity | Unit Rate (SAR) | Total Amount (SAR) | Remarks
SECTION A: EARTHWORK & FOUNDATIONS
A-001 | Site Clearing and Grubbing | m² | 15000 | 45 | 675000 | Including debris removal
A-002 | Excavation for Foundations (Bulk) | m³ | 28000 | 85 | 2380000 | Up to 6m depth
A-003 | Excavation for Foundations (Trenches) | m³ | 5200 | 120 | 624000 | Trench width 0.6-1.2m
A-004 | Backfilling with Selected Material | m³ | 12000 | 65 | 780000 | Compacted to 95% MDD
A-005 | Dewatering System | LS | 1 | 850000 | 850000 | 6-month duration
A-006 | Pile Foundation - Bored Piles (600mm dia) | LM | 8500 | 950 | 8075000 | Depth avg 25m
A-007 | Pile Foundation - Bored Piles (900mm dia) | LM | 3200 | 1450 | 4640000 | Depth avg 30m
A-008 | Pile Cap Construction | m³ | 4800 | 2200 | 10560000 | Grade C40 concrete
A-009 | Raft Foundation (2.5m thick) | m³ | 9600 | 1850 | 17760000 | Grade C50 concrete with waterproofing
A-010 | Ground Improvement - Stone Columns | LM | 6000 | 380 | 2280000 | Grid spacing 2.0m c/c
SECTION B: CONCRETE STRUCTURE
B-001 | Reinforced Concrete Columns (Ground to L10) | m³ | 3200 | 3500 | 11200000 | Grade C60, high-strength
B-002 | Reinforced Concrete Columns (L10 to L30) | m³ | 4800 | 3200 | 15360000 | Grade C50
B-003 | Reinforced Concrete Columns (L30 to Roof) | m³ | 2400 | 2900 | 6960000 | Grade C40
B-004 | Reinforced Concrete Slabs (Post-tensioned) | m³ | 18500 | 2800 | 51800000 | 250mm thick typical
B-005 | Reinforced Concrete Core Walls | m³ | 7200 | 3800 | 27360000 | 400mm thick, Grade C60
B-006 | Reinforced Concrete Beams | m³ | 5600 | 3100 | 17360000 | Transfer beams at L3 and L10
B-007 | Formwork - Flat Slab | m² | 85000 | 165 | 14025000 | System formwork
B-008 | Formwork - Walls and Columns | m² | 42000 | 195 | 8190000 | Steel formwork
B-009 | Steel Reinforcement (Grade 60) | Ton | 9500 | 4200 | 39900000 | Cut and bent to schedule
B-010 | Post-Tensioning System | Ton | 850 | 18500 | 15725000 | Multi-strand system
SECTION C: MECHANICAL, ELECTRICAL & PLUMBING
C-001 | HVAC System - Central Chilled Water Plant | LS | 1 | 8500000 | 8500000 | 4x500 TR chillers
C-002 | HVAC System - AHU and Ductwork | LS | 1 | 6200000 | 6200000 | All floors
C-003 | Electrical - HV Switchgear (13.8kV) | Set | 2 | 1850000 | 3700000 | Main incoming
C-004 | Electrical - Transformers (2000kVA) | No. | 4 | 620000 | 2480000 | Dry type
C-005 | Electrical - LV Distribution Boards | No. | 85 | 45000 | 3825000 | All floors
C-006 | Electrical - Generator Set (2000kVA) | No. | 2 | 2800000 | 5600000 | Diesel, with ATS
C-007 | Fire Fighting - Sprinkler System | LS | 1 | 4200000 | 4200000 | All floors including basement
C-008 | Fire Fighting - Fire Pump Station | LS | 1 | 1650000 | 1650000 | Diesel + electric + jockey
C-009 | Plumbing - Water Supply System | LS | 1 | 3100000 | 3100000 | Includes booster pumps
C-010 | Plumbing - Drainage System | LS | 1 | 2400000 | 2400000 | Including grease traps
C-011 | Elevator Installation - High Speed | No. | 6 | 2200000 | 13200000 | Speed 4m/s, 21-person
C-012 | Elevator Installation - Service | No. | 3 | 980000 | 2940000 | Speed 2.5m/s, freight
C-013 | BMS - Building Management System | LS | 1 | 3500000 | 3500000 | Integrated system
SECTION D: FACADE & EXTERNAL WORKS
D-001 | Curtain Wall System - Unitized | m² | 32000 | 2850 | 91200000 | Double glazed, low-E
D-002 | Aluminum Cladding Panels | m² | 8500 | 950 | 8075000 | Powder coated
D-003 | Stone Cladding - Granite | m² | 4200 | 1200 | 5040000 | 30mm thick, honed finish
D-004 | External Landscaping | LS | 1 | 2800000 | 2800000 | Including irrigation
D-005 | External Roads and Parking | m² | 18000 | 280 | 5040000 | Asphalt with line marking
D-006 | Boundary Wall and Fencing | LM | 850 | 1500 | 1275000 | Precast concrete 3m high
SECTION E: PRELIMINARIES & GENERAL
E-001 | Site Establishment and Mobilization | LS | 1 | 4500000 | 4500000 | Offices, stores, utilities
E-002 | Project Management Staff | Month | 36 | 280000 | 10080000 | 36-month duration
E-003 | Insurance - CAR Policy | LS | 1 | 1200000 | 1200000 | All risks
E-004 | Performance Bond | LS | 1 | 850000 | 850000 | 10% of contract value
E-005 | Health & Safety Provisions | Month | 36 | 95000 | 3420000 | Full-time HSE team
E-006 | Quality Control & Testing | LS | 1 | 1800000 | 1800000 | Lab and field testing
E-007 | Temporary Works - Tower Crane (2 nos) | Month | 30 | 180000 | 5400000 | Luffing jib type
E-008 | Temporary Works - Hoists & Scaffolding | Month | 24 | 120000 | 2880000 | Including maintenance
|  |  |  | GRAND TOTAL (SAR): | 461359000
|  |  |  | VAT (15%): | 69203850
|  |  |  | TOTAL WITH VAT (SAR): | 530562850

## Project Schedule
PROJECT SCHEDULE - Al Nakheel Tower
Phase | Activity | Start Date | End Date | Duration (Days) | Dependencies | Status | % Complete
Pre-Construction | Design Finalization | 01-Jan-2024 | 28-Feb-2024 | 59 | - | Completed | 100%
Pre-Construction | Permits & Approvals | 15-Jan-2024 | 30-Apr-2024 | 106 | Design | Completed | 100%
Pre-Construction | Site Mobilization | 01-Mar-2024 | 31-Mar-2024 | 31 | Permits | Completed | 100%
Substructure | Excavation & Earthwork | 01-Apr-2024 | 30-Jun-2024 | 91 | Mobilization | In Progress | 75%
Substructure | Piling Works | 15-Apr-2024 | 31-Aug-2024 | 138 | Excavation (partial) | In Progress | 60%
Substructure | Pile Caps & Raft Foundation | 01-Jul-2024 | 30-Nov-2024 | 153 | Piling | Not Started | 0%
Substructure | Basement Structure (B3 to B1) | 01-Sep-2024 | 28-Feb-2025 | 181 | Raft Foundation (partial) | Not Started | 0%
Superstructure | Core & Columns (Ground to L10) | 01-Dec-2024 | 30-Apr-2025 | 151 | Basement (partial) | Not Started | 0%
Superstructure | Core & Columns (L10 to L30) | 01-Mar-2025 | 31-Aug-2025 | 184 | Ground-L10 | Not Started | 0%
Superstructure | Core & Columns (L30 to Roof) | 01-Jul-2025 | 31-Dec-2025 | 184 | L10-L30 | Not Started | 0%
Superstructure | Post-Tensioned Slabs (All Floors) | 01-Feb-2025 | 30-Nov-2025 | 302 | Columns (per floor) | Not Started | 0%
MEP | MEP Rough-In (Underground) | 01-Oct-2024 | 31-Jan-2025 | 123 | Basement Structure | Not Started | 0%
MEP | MEP Rough-In (Tower) | 01-Apr-2025 | 28-Feb-2026 | 334 | Slabs (per floor) | Not Started | 0%
MEP | MEP Testing & Commissioning | 01-Jan-2026 | 30-Jun-2026 | 181 | MEP Rough-In | Not Started | 0%
Facade | Curtain Wall Installation | 01-Jun-2025 | 31-Mar-2026 | 304 | Superstructure (per floor) | Not Started | 0%
Facade | Cladding & External Finishes | 01-Sep-2025 | 30-Jun-2026 | 303 | Curtain Wall (per zone) | Not Started | 0%
Interior | Internal Finishes (Fit-out) | 01-Sep-2025 | 30-Sep-2026 | 395 | MEP Rough-In (per floor) | Not Started | 0%
Interior | Elevator Installation | 01-Jun-2025 | 31-May-2026 | 365 | Core Complete | Not Started | 0%
External | Landscaping & Hardscaping | 01-Apr-2026 | 30-Sep-2026 | 183 | External Structure | Not Started | 0%
External | External Roads & Parking | 01-Mar-2026 | 31-Aug-2026 | 184 | Landscaping (partial) | Not Started | 0%
Completion | Snag List & Defects | 01-Jul-2026 | 30-Nov-2026 | 153 | All Works | Not Started | 0%
Completion | Final Inspection & Handover | 01-Oct-2026 | 31-Dec-2026 | 92 | Snag List | Not Started | 0%
Completion | Defects Liability Period Start | 01-Jan-2027 | 31-Dec-2027 | 365 | Handover | Not Started | 0%

## Cost Summary
COST SUMMARY BY CATEGORY
Category | Budgeted Amount (SAR) | Committed Amount (SAR) | Variance (SAR) | Variance %
A - Earthwork & Foundations | 52850000 | 54200000 | 1350000 | 2.554%
B - Concrete Structure | 138500000 | 141200000 | 2700000 | 1.949%
C - MEP Systems | 52350000 | 50800000 | -1550000 | -2.961%
D - Facade & External Works | 107530000 | 109400000 | 1870000 | 1.739%
E - Preliminaries & General | 22830000 | 23100000 | 270000 | 1.183%
Contingency (5%) | 18703000 | 18935000 | 232000 | 1.24%
Design Fees | 8500000 | 8500000 | 0 | 0%
Project Management Fee | 6200000 | 6200000 | 0 | 0%
TOTAL PROJECT COST | 407463000 | 412335000 | 4872000 | 1.196%