## Schedule
PROJECT SCHEDULE & DELIVERABLES TRACKER
Project: Jeddah Mall Renovation - Phase 2
Task ID | Phase | Deliverable / Milestone | Responsible Party | Start Date | End Date | Duration (days) | Status
T-001 | Design | Architectural drawings - final issued for construction | Design Consultant | 2025-03-01 | 2025-04-15 | 45 | Completed
T-002 | Design | MEP shop drawings approval | MEP Subcontractor | 2025-04-01 | 2025-05-10 | 39 | Completed
T-003 | Design | Structural calculations sign-off | Structural Engineer | 2025-03-15 | 2025-04-30 | 46 | Completed
T-004 | Procurement | Long-lead items - chillers and AHUs ordered | Procurement Team | 2025-04-20 | 2025-06-30 | 71 | Completed
T-005 | Procurement | Marble and stone shipment delivered to site | Logistics | 2025-05-15 | 2025-08-20 | 97 | In Progress
T-006 | Construction | Demolition of existing finishes | Main Contractor | 2025-05-01 | 2025-06-15 | 45 | Completed
T-007 | Construction | Structural reinforcement to second floor | Main Contractor | 2025-06-01 | 2025-08-30 | 90 | In Progress
T-008 | Construction | MEP first fix completion | MEP Subcontractor | 2025-07-15 | 2025-10-30 | 107 | In Progress
T-009 | Construction | Facade glazing installation | Specialist Contractor | 2025-09-01 | 2025-12-15 | 105 | Not Started
T-010 | Construction | Internal finishes - tiling and painting | Main Contractor | 2025-11-01 | 2026-02-28 | 119 | Not Started
T-011 | Construction | Joinery and fit-out works | Specialist Contractor | 2025-12-01 | 2026-03-30 | 119 | Not Started
T-012 | Testing | MEP commissioning and testing | MEP Subcontractor | 2026-02-01 | 2026-04-15 | 73 | Not Started
T-013 | Testing | Fire and life safety testing | Civil Defense | 2026-03-15 | 2026-04-30 | 46 | Not Started
T-014 | Handover | Snagging and defects rectification | Main Contractor | 2026-04-01 | 2026-05-15 | 44 | Not Started
T-015 | Handover | Final handover and documentation | Project Manager | 2026-05-01 | 2026-05-30 | 29 | Not Started

## Cost_Tracking
BUDGET vs ACTUAL COST TRACKING
Cost Code | Category | Budget (SAR) | Actual to Date (SAR) | Variance (SAR) | Variance %
CC-100 | Design & Consultancy | 1850000 | 1920000 | -70000 | -3.784%
CC-200 | Demolition Works | 2400000 | 2350000 | 50000 | 2.083%
CC-300 | Structural Works | 8500000 | 6200000 | 2300000 | 27.06%
CC-400 | MEP Installation | 14750000 | 9850000 | 4900000 | 33.22%
CC-500 | Facade & Glazing | 6800000 | 0 | 6800000 | 100%
CC-600 | Internal Finishes | 9200000 | 0 | 9200000 | 100%
CC-700 | Joinery & Fit-out | 4650000 | 0 | 4650000 | 100%
CC-800 | Testing & Commissioning | 850000 | 0 | 850000 | 100%
CC-900 | Project Management | 2100000 | 1240000 | 860000 | 40.95%
TOTAL |  | 51100000 | 21560000 | 29540000 | 57.81%